MACLOUD quarterly catch-up meeting
Wednesday 14 January 2026, 1.30pm via Teams 
In Attendance 
Jim Haywood (Exeter) JMH – Chair 
Zhiqiang Cui (Leeds) ZC
Daniel Partridge (Exeter) DP
Ken Carslaw (Leeds) KC
Laura Wilcox (Reading) LW
Paul Halloran (Exeter) PH
Paul Field (Leeds) PF
Sarah Smith (Oxford) SS
Shinto Roose (Reading) SR
Robin Chawick (Exeter) RC
Sam Blackburn (Exeter) SB
Philip Stier (Oxford) PS (joined mtg at 2pm)

Apologies
Brittany Dygert (Exeter) BD
Monisha Subbiah Renganathan (Exeter) MSR
Paul Connolly (Manchester) PC

JH opened the meeting and welcomed post-docs Sarah Smith (Oxford), who will be working with Philip Stier, and Shinto Roose (Reading), who will be working with Laura Wilcox.

Apologies were received from Exeter’s post-docs, Brittany Dygert and Monisha Subbiah Renganathan as they were attending MACLOUD related meetings today.

1) Review of Action Items from previous minutes
· LW to ask at Reading if it’s possible to run simulations beyond 2100. LW to send JH plot details before asking Steve Rumbold for diagnostics.			ACTION ONGOING – LW
· JHM to send PH full list of diagnostics.				ACTION ONGOING – JMH
· Development of MACLOUD website, see update in 3 below.
· JMH to try and keep quarterly meetings to one hour duration unless there are significant results to discuss.

2) Update on recruitment and activities :
a. WP1: Fundamental  understanding through explicit process modelling, Connolly
DP has been involved in this work supporting configuration and ensuring we have key diagnostics. Feedback has been requested from sea-spray evaluation scheme. 
ParSec framework has been finalised.

PC provided the following email update after the meeting - WP1 progress has been limited this period, but we’ve had a discussion on WP1.1 how aerosol-associated water is represented in CASIM and the associated latent heating/cooling when spray evaporates.

We currently have two implementable treatments to compare:

· Treat injected spray water as fully evaporating to vapour (full latent cooling).
· Account for retained particle-bound water at ambient RH, reducing the latent 		cooling accordingly.

b. WP2: High-Resolution Modelling, Stier/Field
SS is able to run the model in her second week of starting her post. 
ZC talked through his finding related to a research paper by Rasch et al. 2024 target regions looking at cloud droplets. The next step is to explore different ship tracks and ship speeds.
DP to send PF details of new activate scheme.			ACTION – DP
PF to send DP link to suite.					ACTION - PF
JH suggested looking at mixed meteorological states as opposed to concentrating on stratocumulus regions and directed people to Alex Mason’s recent paper which can be found on the MACLOUD website.
c. WP3: GCM simulations & design, Haywood
JMH presented a PowerPoint with an update on WP3.
As mentioned above Alex Mason has recently published a paper which can also be found here - https://doi.org/10.5194/egusphere-2025-5591
MSR has been delayed in her work running the baseline simulations. 
BD is now in place and is attending UKCA training in Leeds today.
d. WP4: Impacts - Physical climate responses, Wilcox
LW confirmed that work hasn’t yet started but Shinto Roose has been recruited and will start in 2 weeks’ time. LW asked if they should be looking at other simulations whilst waiting for project specific simulations? JMH suggested looking at GEOMIP and will send LW a list of suite IDs.						ACTION – JMH

e. WP5: Impacts - Earth System Responses, Halloran
Nothing to report to date as work is waiting on model runs from BD.

f. General other University Specific activities
Nothing to report.

3) Update on website (Haywood) > MACLOUD
SB has created a website for MACLOUD which can be accessed using the above link. Any items that group members would like to be included should be sent to SB.

4) Update on NERC Oversight Group Report (Haywood)
Draft report has been completed and comments requested. Public perception has been much more positive than perhaps some would have thought. Generally positive about research into SRM but more cautious about deployment.

5) Update on NERC cross-theme coordination (Haywood) 
Process has been time consuming due to JASMIN/MONSOON access. LW volunteered to proofread the diagnostics and send to JMH.				ACTION - LW

6) Update on NERC carbon budget reporting (Haywood)
Report has been completed, and NERC seem happy with the input received. 

7) Update on meetings (Haywood)
a. GeoMIP 2026, 17th – 19th March, Kyoto.

b. GeoMIP 2027, date to be confirmed, likely around Easter.

c. RMS, Wednesday 25th March, pm, Exeter: hybrid – will focus on SRM.

d. EGU, 3-8 May 2026, Vienna/hybrid.

e. GRC 2026, 21st – 26th June, Maine, USA.

8) AOB
PS informed attendees of the EarthCARE workshop taking place 8-12 June 2026 in Oxford. PS will circulate further information when available.				ACTION - PS

9) Date of next meeting
JMH to move next meeting to 21 or 22 April to ensure the meeting does not fall within Easter holidays.								ACTION - JMH



				
		
